## Feb 2024
Date | Day | Project Name | Tasks | Start Time | End Time | Status | Assigned By | Assigned To | Assigned Date | Expected Date | Remarks
2024-02-27 | Tuesday | Dashboard UI Design | Following Pages design I have done today | 9:30 | 18:30
1) Payment Statement (Design part is complete)
2) Payout Statement (Design part is complete)
3) Main Wallet (Responsive part is pending)
4) Error 404 page design
5) Pagination and filter column added in Dashboard transaction tables
2024-02-28 | Wednesday | Dashboard UI Design | Following pages design has been done | 9:30 | 18:30
1) Callback token
2) Api Documents
3) Main wallet page responsive
4) Custom Pagination added in all pages where is required
5) Menu Icon has been switched from right to left in Header for mobile view
6) Overall Frontend dashboard is completed
2024-02-29 | Thursday | New Project (UI Design of Exchange Trading) | 1) Homepage Design is Complete (Responsive) | 12:00 | 18:30
2) Exchange design page also made (Responsive) (10% part is pending)
|  |  | 1) Made a forgot password api (60% done) (Previous Dashboard project) | Before 12:00 PM

## March 2024
Date | Day | Project Name | Tasks | Start Time | End Time | Status | Assigned By | Assigned To | Assigned Date | Expected Date | Remarks
2024-03-01 | Friday | New Project (UI Design of Exchange Trading) | 1) Exchange design is completed and dynamically added currency conversion for USD to INR | 9:30 | 18:30
2) Change Account design page is added
3) Review Order page is added
4) Send Money section design is also completed
5) Select Recipeint list is added
6) My Account design is also added
7) Add Account page is also added (company signup page is complete with dynamic list of country flag selected , currency code is also reflected when user select country)
Screenshot is attached on mail for above points
|  |  |  | 9:30 | 18:30
2024-03-02 | Saturday | New Project (UI Design of Exchange Trading) | 1) Make cards page design
2) Online paymnets page design
3) Team members page design
4) All accounts page design (This page open when user click in Right top icon in Home Page)
5) Account details page design (Copied functionality also done)
6) Sidebar added for mobile view
1 point is still pending in online statement part
2024-03-04 | Monday | New Project (UI Design of Exchange Trading) | 1) Make online payment design (Responsive also done) | 9:30 | 18:30
2) Add title wise page dynamically
3) Account Statement page made
4) Swapping of exchange two currency values design also implemented
I have attached screenshots with recording
Two types of recording added
1) Whole website recording
2) Responsive Wise recording
2024-03-05 | Tuesday | Dashboard UI Design | 1) Admin Dashboard has been setup | 9:30 | 18:30
2) Permission Page has been made (Design) for sidebar pages (Dynamic part is pending)
3) Dynamic Logo has been updated for user dashboard
4) Forgot Password has been done for user logins
5) Reset password page has been added
6) Admin profile page has been made and done dynamically updated ,could upload profile image and save their details
Backend Task:-
1) Admin Register api has been made
2) Admin login / logout api has been made
3) Admin Change password api has been made
4) Admin profile details api has been completed
5) Users list api has been made and integrated in admin dashboard page
6) Reset Password link has been sent to the respective user registered E-Mail Address
7) Profile upload api has been made (Admin)
2024-03-06 | Wednesday | Dashboard UI Design | 1) Permission Page : | 9:30 | 18:30
1) List of permission assigned accroding to role added
2) Edit functionality added
2) Role Page:
1) Role page has been added (Design)
2) Add / Edit and delete functionality has been added
3) User List Page
1) User page has been added
2) User list id dynamically working (rest of the things are pending)
Backend Work
1) Create / Edit / Delete api has been added for role section
2) Roles list api has been added
3) Permission edit / assigned api has been made
4) modification in user api also
5) Permission list api has been added
User Sidebar is now dynamically controlled by Admin
2024-03-07 | Thursday | Dashboard UI | 1) User List page has been done dynamic (Edit / View) functionality added | 9:30 | 18:30
2) Add pagination also
|  | Currency Exchange | 1) Login and register page has been added
2) Live the frontend part
nodejs and react setup has been done on live
Mongo database setup is pending
URL: https://xeyso.com/react
2024-03-08 | Friday | Currency Exchange | 1) Login and Register api has been made
2) Login / logout / register page has now are dyanmic , user can register and login
Above things are working in local machine
Mongodb is not connecting in live server, because bt default cpanel block th port 27017
ssh login is also not connecting , I tried to login through putty ssh login but not connected (Screenshots has been attached)
I will R&D two more days regarding connection of mongodb in cpanel
|  |  | Backend Task | 9:30 | 18:30
2024-03-11 | Monday | Currency Exchange | 1) Made api for add / edit / list / getbyid account
2) Made api for default account
3) Made api for currency exchange (calculation of currency value)
4) Made api for fetching currency and update into the database (In order to less use of api calls)
5) Made api for currency add in case of currency not exists I our record
Frontend Task
1) All account list dynamic in front end
2) Select accountfrom list and get result dynamically
2024-03-12 | Tuesday | Currency Exchange | Backend Task | 9:30 | 18:30
1) Made api for recepient add/edit/udpate/getdetails by id
2) Made api for transaction add/getTransacationlits ./ by id
Frontend
1) All account wise data display
2) Recepent part is dynamic listed
3) Search part is also implemeted on all recepint
4) Exchange currency part is 80% completed
2024-03-13 | Wednesday | Currency Exchange | Backend Task | 9:30 | 18:30
1) Modification in add account api
Frontend Task
1) Design done for add account
2) Exchange currency part is completed with testing done also
live the project on 3.70.98.224/api (need to point again on 3.70.98.224)
2024-04-14 | Thursday | Currency Exchange | Backend Task | 9:30 | 18:30
1) Modification done in add account / edit on controller and model
2) Modification done in recepient account / edit
3) When user signup first time then account also created as per selection of country in resgistration form
Frontend Task
1) Add / Edit Receipient page has been dynamic now
2) Add / Edit Account page has been dynamic now
3) Add functionality if customer have 0 amount on particular account then exchange and send button will disabled
4) Add money page created need to work on full page and api
Edit Account option has been provided on all account page
|  |  |  | 9:30 | 18:30
2024-04-15 | Friday | Currency Exchange | Backend Task
1) Modification in user/account/transaction api
2) Made a transaction api by their respective account
3) Update user profile and get details api
Frontend
1) Made a user profile page
2) Dynamic part is also done In user profile page
3) Transaction page list and per transaction all details view page also made (dynamic)
4) When user change their default currency, then new currency account will create if it doesn'rt exists in our record
5) Live the project on http://13.233.6.49/api
2024-04-16 | Saturday | Currency Exchange | Backend Task | 9:30 | 18:30
1) Made a api for member (Edit/Add/getdetails/delete
2) Validate api for member login
3) When Member login otp will receive on their registered email id (api done)
Frontend
1) My account page has been done dynamic
2) Team Members page has been done dynamic
3) Filter part is pending ion team members page
4) Validation part is done at home page where user select account
5) Sell order is done
2024-04-18 | Monday | Currency Exchange | Task | 9:30 | 18:30
1) Modification done in members api
2) Modification done in user login and member alogin api (Added permission list and user type on access token)
3) Modify api Add filters in Members list (by daty, week , 15 days , month and Custom)
4) Add link in see all link (dynamic)
5) Add permisison for member login (Sidebar elements come in permission)
All changes and work till date has been pushed on live server. (http://13.233.6.49/api)
|  |  |  | 9:30 | 18:30
2024-04-19 | Tuesday | Currency Exchange (Project Completed) | Task
1) Transaction api has been corrected
2) Get statement api has been made
3) New Exchange api has been integrated in fronend (Rapid api)
4) put validations on email/mobile fields in all forms (user profile,Add/edit recepient and members page
5) Account statement has been generated in pdf format and maild to the customer mail id
2024-04-20 | Wednesday | Currency Exchange (MUI) | Task | 9:30 | 18:30
Currency Exchange project
Frontend Tech: (React, vite and MUI)
1) Sign In
2) Sign Up
3) Dashboard (Sidebar, RightBar)
Other designs part screenshot Attached in mail
|  |  |  | 9:30 | 18:30
2024-04-21 | Thursday | Currency Exchange (MUI) | Task
1) Change Account pop up made when user click on select account
2) Order review page made when user click on review order
3) All accounts page has been designed with responsive
4) Account info page also made when user click on particular account (click to copy fuctionality also impletented)
5) Change account name pop up also added
6) Add and Edit Account page also designed
7) All page are fully responsive
2024-03-22 | Friday | Currency Exchange (MUI) | Task | 9:30 | 18:30
Made a technical document
Made a User Profile Page
Made a Statement page
2024-03-26 | Tuesday | Currency Exchange(MUI) | Task | 9:30 | 18:30
Design a Payment Page
Design a Account Statement Page
Design a Cards Page
Design a Member Page with Add member also
My Account page has been also completed including responsive for all sizes
Add and Edit Receipient page has also been designed
Frontend Designs task has been completed with the help of MUI library
|  |  |  | 9:30 | 18:30
2024-03-27 | Wednesday | Currency Exchange (MUI) | Task
Updated project on live server
Url: http://13.233.6.49/mui/
|  | Currency Exchange (Tailwind CSS) | Task
Test and modify user login time of authenticate user, after 12h token will expire
Sometime exchange api will give response in a seconds or 10 seconds so in that case I have added loader there
Correct design part in exchange currency window, fixed the size of right hand side
pdf for account statement is working on local but error in server, that issue has been resolved and tested
Add functionality in add member by user, once member added by user then a email will be forwarded to the member with their login credentials
current allignment issue in account info page
All changes has been updated in live server
|  |  |  | 9:30AM | 6:30PM
2024-03-28 | Thursday | Currency Exchange (Tailwind Css) | Task
Changes done in All Transactions list page and Members list table ui
Add protected route in all pages.
2024-03-29 | Friday | Currency Exchange (Tailwind Css) | Task
|  |  | Implement dark mode feature on project | 9:30 | 18:30
Waiting for Task MUI changes from JavaScript to TypeScript
|  |  |  | 9:30 | 18:30
2024-03-30 | Saturday | Currency Exchange (MUI) | Task
Converted jsx files to tsx of MUI project
Dark theme mode features also implemented
Transaction List page remaining

## April 2024
Date | Day | Project Name | Tasks | Start Time | End Time | Status | Assigned By | Assigned To | Assigned Date | Expected Date | Remarks
2024-04-01 | Monday | Currency Exchange (MUI+TYPESCRIPT) | 1) Converted all jsx files into tsx | 9:30 | 18:30
2) Added a forgot password page
3) Pending Transaction list also completed
2024-04-02 | Tuesday | Today I have no task to work on |  | 9:30 | 18:30
2024-04-03 | Wednesday |  | Currency Exchange (MUI_TypeScript) has been live on server | 9:30 | 18:30
http://13.233.6.49/ts
2024-04-04 | Thursday | BlockChain Project (Currency Exchange Project) | Doing Research and Development
Test a few api as get accounts, assetwallets list,assetbalance, users list and create account
Setup a server.js file on local and test these api
2024-04-05 | Friday | BlockChain API (Currency Exchange Project) | Doing R&D | 9:30 | 18:30
2024-04-06 | Saturday | BlockChain API | Doing R&D | 9:30 | 18:30
Test Wallet (External Wallet Api)
Staking API
Initiate Stake Operation
Get staking summary details
Get staking summary details By Position ID
2024-04-08 | Monday | BlockChain / Currency Exchange Project | Review the code of neoconnect frontend v2 github repositories | 9:30 | 18:30
Need more clarification on this.
Need api documentation
2024-04-09 | Tuesday | BlockChain / Currency Exchange Project | Review backend code | 9:30 | 18:30
Now implementing on our project
Made Crypto Exchange Modal design
Implemented websocket market real time data api on postman (wss://stream.binance.com:9443/stream) Parameters: { "method": "SUBSCRIBE", "params": ["btcusdt@miniTicker"], "id": 1 }
implemented 24hour market real time data api on postman (https://api.binance.com/api/v3/ticker/24hr)
2024-04-10 | Wednesday | Currency Exchange Project | Design a Invite (Refer & Reward) and Help Ticket Page
Put a vaildation on Crypto Buy/Sell Modal Page
Design a Card Page and put u validation on expiry date of selection (Past date can't available for selection)
Made a body and Sidebar scrollbar thin skyblue in color
need to do fully dynamic all above pages
2024-04-11 | Thursday | Currency Exchange Project | Re-Design User Profile page | 9:30 | 18:30
Design a new KYC page
Put a validation in kyc page as I integrated stepper functionality
All work till today updated on liver Server
Custom date range added in statement page
Content Copy functionality added in account info page
Live Website Url: http://13.233.6.49/ts/home
2024-04-12 | Friday | Currency Exchange Project | Made a Error 404 page | 9:30 | 18:30
Small bug fix in sidebar page (In mobile when user click on any sidebar item page nvaigate but sidebar remain open, so I fixed it )
Fix responsive part in User Profile, Kyc , help center , Rewards and Statement page
Setup Backend part
Login and logout dynamic part has been implemented
Jwt Authorization code has been implemented in login page
2024-04-15 | Monday | Currency Exchange Project | All Account part has been done dynamic | 9:30 | 18:30
Exchange window is fully dynamic now
Review order window part has been done also dynamic
Transaction for exchange window has been also done dynamic
Reciepients list in home page / Dashboard part is dynamic now
Modify design of User Profile page
Transaction list in homepage also has been done dynamic
2024-04-16 | Tuesday | Currency Exchange Project | All Transaction list page has been done dynamic with pagination functionality | 9:30 | 18:30
Per Transaction view page details are also working now
Put validation on Exchange button when user have 0 amount in their selected account / default account
All accounts list is now dynamically get results/ Account info
Default tag is showing in their respective accounts list
Selected Account info showing dynamic content now
Account Number and ifsc Code copy to clipboard is working now
Search account by name is working (Dynamically implemented) ( Account List Page/Window)
My Accounts page has been also done dynamic
2024-04-17 | Wednesday | Currency Exchange Project | Made a crypto page | 9:30 | 18:30
Design a New company list page
Made a Add Money Modal box in Home Page
Select Recipioent page has been done dynamic
Edit Receipient page info has been done dynamic
Default Account change functionality has been implented on My Account page
2024-04-18 | Thursday | Currency Exchange Project | Search functionality has been implemented on recepient list page | 9:30 | 18:30
Add Account page has been done dynamic
Edit Receipient page has been also done dynamic
Edit Account page has been also done dynamic
Made a api for Card page
1) Add Card details
2) Update Card Details
3) Delete Card
4) Get info of selective card
5) Get all cards list
Modify Card Details Page (Dynamic card view implemented)
Add Card/Delete has been implemented on frontend Side
SignUp / Register has been added and implmented
All Card list page has been added
2024-04-19 | Friday | Currency Exchange Project | Add Member page is dynamically implemented | 9:30 | 18:30
view Member list also implemented
Edit Member / Add Member are also implemented dynamically
Member login details page has been also designed and dynamically implemented
Filters are also added in Members page (today,last 7 days , 1 Month and custom Range)
Made a api for User Company page
1) Add Company details
2) Update Company Details
3) Delete Company
4) Get info of selective Company
5) Get all company list
Company details & Company List Add page has been added with dynamic functionality
2024-04-20 | Saturday | Currency Exchange Project | User profile page has been modified | 9:30 | 18:30
User Details has been dynamically saved now
User details api has been updated & modified
Company Selective list view details has been upadted (Modal box)
Company detaild edit dynamically has been completed now
Receipient Add fuctionality has been implented & completed
All above work is updated on live server as on till date
2024-04-22 | Monday | Currency Exchange Project | Card Details Edit page has been completed | 9:30 | 18:30
Add money to wallet api kas been made
List of add money transactions has been completed
Pagination code has been modified in Transaction List Page
Buy/Seel Crypto page has been also dynamic
Buy/Sell Crypto History list are dynamic now
Put a Rate limit time in login api (Maximum 5 attempts of login can accept after that user can login after 1 hour)
2024-04-23 | Tuesday | NeoConnect Project | Support Ticket Api has been created | 9:30 | 18:30
Add Support ticket / All list support ticket by user api created
Both of the above api is also implented on frontend support page
Kyc Api has been created
Kyc Frontend Page has been dynamically implemented
2024-04-24 | Wednesday | NeoConnect Project | Small bug fix in user profile page | 9:30 | 18:30
Account Statements page has been done dynamic
If Selected accounts has an transaction on selected period then a pdf has been sent to the registered email id of user
Reset Password & Forgot Password page has been dynamic now
Change Account name API has been integrated
Crypto Wallet Buy/Sell page has been done dynamic
Request Wallet Address API has been created
Request Wallet Address page has been done dynamic with integration of API
Referal Code generated and updated in user table (API Created)
2024-04-25 | Thursday | NeoConnect Project | Get Refer by users list api has been created | 9:30 | 18:30
Generate refer code api has been integrated in frontend page
Signup from Referal link functionality has been done in signup Page
Refered Users list on page Refer & Rewards are dynamic now
Export as pdf & excel functionality has been added Transaction list table
Fix error in Transaction list by account
Email template created for member login credentials at the time of member created by the user
Member login page has been created and page dynamic too
Receipient type field has been added in edit receipient form
Add / Edit Tax page has been designed
Member login page has been created and page dynamic too
2024-04-27 | Saturday | NeoConnect Project | Changes done in Company Details page like responsive issue and image update issue | 9:30 | 18:30
Bug fix in card expiry date like (MM/YY) format
No data found svg image has been setup on every data table when table has no data
Add / Edit/ Delete Tax Api has been created
Add / Edit / Delete Tax page has been dynamically set
Now Working on Invoices Module
2024-04-29 | Monday | NeoConnect Project | Payment QR Code Api created (Add/Edit/Delete) | 9:30 | 18:30
get list all payment qr code api also created
Payment Qr Code Api is integrated with frontend also
Invoice Templates Design has been made for following countries
1) Default Invoice Template
2) Toronto Invoice Template
3) Rio Invoice Template
4) London Invoice Template
5) Istanbul Invoice Template
6) Mumbai Invoice Template
7) HongKong Invoice Template
8) Tokyo Invoice Template
9) Paris Invoice Template
10 NewYork Invoice Template
2024-04-30 | Tuesday | NeoConnect Project | Invoice Template Settings content update dynamically | 9:30 | 18:30
Add Invoice Page has been designed
Invoice List page has been designed
Dynamic task ha been done in Add Invoice Page like
1) get All Tax list
2) Dynamically add more products with qty,price
3) Also done calculation of all subtotal , total (Testing is going on)

## May 2024
Date | Day | Project Name | Tasks | Start Time | End Time | Status | Assigned By | Assigned To | Assigned Date | Expected Date | Remarks
2024-05-01 | Wednesday | NeoConnect Project | Add Invoice Calculation of product (Invoice) added has been completed and tested also | 9:30 | 18:30
Discount, Multiple Taxes has also been added in invoice dynamically
Add invoice data has been also saved in to the database
edit invoice data 70% completed
2024-05-02 | Thursday | NeoConnect Project | Edit invoice part has been completed | 9:30 | 18:30
All Invoice list part also has been completed
Transaction all list bug has been corrected
When Invoice generated a invoice pdf will sent to the user email id
Start and Stop Recurring funtionality also implemented on Invoice list page
Edit/delete.copy invoice url functionality has been also added in invoice list page
2024-05-03 | Friday | NeoConnect Project | Invoice pdf generated | 9:30 | 18:30
Save and send button work is completed on add invoice page
Filter option has been added in Invoice List Page
Filter option functionality has been implemented
2024-05-04 | Saturday | NeoConnect Project | Reset filter has been Implemented | 9:30 | 18:30
Small changes fix in Edit Invoice Page
Responsive has been done on page Add Invoice and Edit Invoice
New York City Invoice template has been created
Default Invoice Template has been created
fix bug in invoice calculation values
Close button has been added on filter options modal box
Toronto Invoice Template pdf has been created dynamically
Rio City Invoice Template pdf has been created dynamically
London City Invoice Template pdf has been created dynamically
Istanbul City Invoice Template Pdf has been created dynamically
Mumbai City Invoice Template Pdf has been created dynamically
2024-05-06 | Monday | NeoConnect Project | Paris City Invoice Template Pdf has been created dynamically | 9:30 | 18:30
Tokyo City Invoice Template Pdf has been created dynamically
HongKong City Invoice Template Pdf has been created dynamically
Invoice Template by default color has been set on all invoice dynamically
Invoice Settings page has been designed (70% completed)
2024-05-07 | Tuesday | NeoConnect Project | Invoice Settings API (Add/Update/Get Details) has been created | 9:30 | 18:30
Invoice Settings Page has been implemented dynamically
Excel Export and Pdf Export functionality has been implemented in Invoices List Page
Add money bug fixed in Dashboard page
2024-05-08 | Wednesday | NeoConnect Project | Spot page has been created | 9:30 | 18:30
websocket has been intergrated for getting values of coin trades
Real time chart has been integrated in Spot page
2024-05-09 | Thursday | NeoConnect Project | Spot page has been implemented dynamic (60%) | 9:30 | 6:30PM
coins list added in select box in spot page
Recent Trades are realtime when switch to another coin it will reflect their coin related data
Chart will also show dynamic realtime candles
2024-05-10 | Friday | NeoConnect Project | Icons added in spot page on icons select box | 9:30AM | 6:30PM
Orders History , Open History and Trade History tab added in spot Page
Dark/Light theme mode bug fixed for sidebar
Changes done in Add Tax/Edit Tax page
Tax field remove from Add Invoice/ Edit Invoice Page
2024-05-13 | Monday | NeoConnect Project | Default QR bug is fixed on QR Payment Page | 9:30AM | 6:30PM
Excel Export bug fixed in Invoice Page
Export Excel issue also fixed on Transaction List and Refer and Rewards Page
Error fix (Action buttons showing similar data) in Company Details page
Login Bug Fixed
Dark mode bug fixed in cards list , company details, invoices , members and statements page
Default Tax bug is fixed on QR Payment Page
2024-05-14 | Tuesday | NeoConnect Project | Admin Setup has been added | 9:30AM | 6:30PM
Login Page has been designed
Dashboard Page has been designed
1) User, Enquires and Spot Trades Added
2) Market Overview chart has been added accroding to selection of coin (Dynamically working)
3) Coin Pairs stats has been implmented on dashboard page (Dynamically listing coins pair statistics)
Spot page has been added with Add Coin and Add Coin Pairs modal box has been also designed
Wallet Request Page has been also designed
Referrals page has been added
Users KYC list page has been added
User Management List Page has been added
2024-05-15 | Wednesday | NeoConnect Project | Tickets Supports page has been created | 9:30AM | 6:30PM
Transactions page has been created
Fee Structure Page has been designed
Profile Page has been created
Two Factor Authentication design has been added in Admin Profile Page
Bakend Task
1) Admin Register api has been created
2) Admin Login Api has been created
3) Admin Profile update api has been created
4) Get Admin info api has been created
5) Admin Logout api has been created
6) Change password api has been created
7) Forget password api has been created
8) Reset Password api has been created
9) Get all users list api has been created
10) Base Coin add/edit/delete api has been created
11) Get All base code details api has been created
12) get particular base coin details api has been created
2024-05-16 | Thursday | NeoConnect Project | 1) Coin Pairs add/edit/delete api has been created | 9:30AM | 6:30PM
2) Get All lists of Cin Pair api has been created
3) Get coin pair details by id api has been created
4) Wallet Request List Api has been created
5) Wallet request status update api has been created for admin
6) Referral list api has been created for admin
7) Kyc list api has been created for admin
8) Support ticket list api has been created
9) Support status update by the admin api has been created
10) Wallet Address Request api has been implemented on wallet address page (Admin)
11) Wallet Request overall history for particular request api has been created
12) Wallet Request api has been integrated on wallet request page
13) Kyc Status update api has been created
14) Kyc updated status history list api has been created
15) Kyc history and updated request api has been integrated in admin
16) Filter api created for kyc list has been created and also added on kyc page (Admin)
2024-05-17 | Friday | LEAVE
2024-05-18 | Saturday
2024-05-20 | Monday | NeoConnect Project | Re-design Admin Login Page | 9:30AM | 6:30PM
Profile update api is integrated on profile page
Two Factor Authentication api has been integrated in admin profile page
Two factor Authentitcation
1) send otp api has been created
2) verify otp api has been created
3) Match otp and update two factor field api has been created
Admins list page has been created where superadmin can manage all admins login
Update admin with auto reset password functionality has been added
Superadmin also created where number of admins could be created and managed
2024-05-21 | Tuesday | NeoConnect Project | No of Users in dashboard page has been dynamic | 9:30AM | 6:30PM
No of Enquiries/Tickets has been added in dashobard page
Tickets list api has been integrated
Filters functionality has been done dynamic now in Tickets List
Support History list Api for particular request has been created
Support Ticket Status update api has been created
User Management action options added like update user status and view particular user info
2024-05-22 | Wednesday | NeoConnect Project | Status update functionality implemented directly from users listing page | 9:30AM | 6:30PM
User Login Session history api has been created and implemented on login page
User session api like add, update and get session history api has been created
Members List api has been created and implmented also in User Management Page (Admin)
Invoice List api has been created and implmented also in User Management Page (Admin)
Accounts List api has been created and implmented also in User Management Page (Admin)
Receipint List api has been created and implmented also in User Management Page (Admin)
2024-05-23 | Thursday | NeoConnect Project | Add Base Coin api has been implemented on Add coin page | 9:30AM | 6:30PM
Add Sport Coin Pairs add/insert api has been also implemented
Coin Pair details more info view modal box has been added in spot page (Admin)
Edit / Update task also completed
Base Coin List also implemented
Fee Structure Add/Edit/Delete Api has been created
Get fee structure list with by id get details API has been created
2024-05-24 | Friday | NeoConnect Project | Admin Fee Structure add/delete api has been implemented | 9:30AM | 6:30PM
Admin Fee Edit also added
Refered By Users Count API has been created
Refered Users list action view also implemented
Error fixed in dark theme mode
Invoice and Transactions part is left in Admin panel
2024-05-27 | Monday | NeoConnect Project | Delete Modal confirmation box has been added | 09:30AM | 6:30PM
Delete modal added in spots, fee structure page
Remove Admin profile image API has been created
Remove profile image api has been integrated in admin profile image
Css changes done in all pages when theme mode is dark
Dynamic Charts has been created in Dashboard Page
2024-05-28 | Tuesday | NeoConnect Project | Coin Pairs Table has been added in Dashboard Page (Full responsive with dynamic content) | 09:30AM | 6:30PM
Invoices Pages created in Admin
Tax page created in Admin
Payment QR Code page has been created
Invoice Templates page has been created
Invoice Settings page has been created
2024-05-29 | Wednesday | NeoConnect Project | Invoice Tax add/edit/delete page has been done dynamically working | 9:30AM | 6:30PM
Payment QR Code add/edit/delete page has been update with dynamic functionality
Invoice Add/edit/delete page has been added and dynamic functionality has been implemented
Invoice Settings page has been removed from users and add in Admin Panel
Changes error 404 page according to active panel it will redirect to that page when click on back button
Payment Gateway Settings page has been added on Admin
Payment Gateway Settings add/update details api has been created
2024-05-30 | Thursday | NeoConnect Project | Razorpay Payment gateway has been integrated | 9:30AM | 6:30PM
Payment Page has been created in User Panel Side
Razorpay payment response api has been created
Invoice update api has been created
Invoice model has been updated
2024-05-31 | Friday | NeoConnect Project | Razorpay Payment has been integrated (100%) | 9:30AM | 6:30PM
Partial, Full payment functionality has been implemented on Invoice (User Panel)
Paypal Payment Gateway has been added (30% Work Completed)

## June 2024
Date | Day | Project Name | Tasks | Start Time | End Time | Status | Assigned By | Assigned To | Assigned Date | Expected Date | Remarks
2024-06-03 | Monday | NeoConnect Project | Paypal Payment Gateway work is completed (100%) | 9:30 | 18:30
Stripe Payment Gateway is also completed (100%)
Stripe payment Response API has been created
Invoice Orders Table has been modified
Payment Page has been modified
Transactions table info has been added in Admin Invoices List Page
2024-06-04 | Tuesday | NeoConnect Project | ITIO Payment gateway has been integrated (70%) | 9:30 | 18:30
New Project has been setup
1) Project Repository has been created on github
2) Admin Panel has been setup on local machine
3) Technology used for project are as follows:
1) React + TypeScript
2) Vite
3) Material UI
4) Login Page, forgot password and reset password page has been added
5) Git Repository Path: https://github.com/mern-itio/AdminPanel.git
2024-06-05 | Wednesday | Admin Panel | 1) Admin Panel dashboard page has been designed | 9:30 | 18:30
2) Messages list page has been created
3) New Message page has been designed
2024-06-06 | Thursday | Admin Panel | 1) Profile list page has been created and designed | 9:30 | 18:30
2) User profile page has been designed
3) Details tab has been created
4) Balance tab has been created
5) Fees tab has been created
2024-06-07 | Friday | Admin Panel | 1) Companies tab page has been created and designed | 9:30 | 18:30
2) Documents tab page has been created and designed
3) Comments page has been created
4) Risk Scores page has been designed
5) Activities page has been designed and created
6) Related Cards page has been created
7) All pages are responsive
2024-06-10 | Monday | Admin Panel | 1) Administrator Tab page has been designed | 9:30 | 18:30
2) Edit Fees page task has been done
3) Related cards issue has been solved
4) Dark mode issues has been solved
5) Responsive issue has been solved
2024-06-11 | Tuesday | Admin Panel | Documents (Upload document modal box with drag & drop functionalities) | 9:30 | 10:30
|  |  | Users List Page | 10:30 | 18:10
|  |  | SSL integration done for http://connect.oyefin.com/ | 14:15 | 14:45
2024-06-12 | Wednesday | Admin Panel / UI Design | Dark Theme issues has been solved for all pages | 9:30 | 13:00
|  |  | Risk Levels Page has been designed | 13:00 | 13:45
|  |  | Risk Levels Fees Export / Import | 14:30 | 16:30
|  |  | Transfers Page has been designed | 16:50 | 17:20
|  |  | Fees table page has been added | 17:30 | 18:25
2024-06-13 | Thursday | Admin Panel / UI Design | Activity log | 9:30 | 10:30
|  |  | External Fee Payment | 10:30 | 12:00
|  |  | External fee payment invoice | 12:00 | 1:40
|  |  | Monitoring | 14:15 | 15:00
|  |  | Crypto AML | 15:00 | 16:30
|  |  | Affiliate User | 16:41 | 16:50
|  |  | Fix Sidebar Issue | 17:00 | 18:00
2024-06-14 | Friday | Admin Panel / UI Design | External Fee Payment (Modal box content when click on action button) | 9:30 | 10:30
|  |  | IBAN page has been designed | 10:30 | 11:10
|  |  | IBAN Request page has been created | 11:10 | 11:30
|  |  | Service Providers page has been created | 11:36 | 13:40
|  |  | Service Fees tabs has been created | 14:20 | 16:25
|  |  | Product page has been created | 16:50 | 17:45
|  |  | Trading desk page has been created | 17:50 | 18:15
2024-06-17 | Monday | Admin Panel / UI Design | Limited Tokens Setting Page | 9:30 | 10:45
|  |  | Document Requested Page | 10:50 | 11:30
|  |  | Document Types(Beta) Page | 11:36 | 12:30
|  |  | Document Types Page | 12:40 | 13:40
|  |  | Edit Modal box in document type page | 14:20 | 16:30
|  |  | Sidebar Issues has been fixed | 16:45 | 17:45
Task allocated at 4 PM
2024-06-18 | Tuesday | Admin Panel / UI Design | Trading Desk Page | 16:00 | 17:00
|  |  | AML Requested Page & AML Requested Filter Modal Box | 17:00 | 17:30
|  |  | Document Types (Beta) Page | 17:30 | 18:05
|  |  | Dynamic Form Page | 18:05 | 18:20
2024-06-19 | Wednesday | Admin Panel / UI Design | Dynamic Form Task (40% task is completed) | 9:30 | 18:30
Now Dynamicaly add component by drag & drop functionality
Dynamically add tabs
2024-06-20 | Thursday | Admin Panel / UI Design | Dynamic Form Task (100% Completed) | 9:30 | 17:30
2024-06-21 | Friday | Admin Panel / UI Design | Add Message page has been created and designed | 9:30 | 10:30
|  |  | Fee Summary Page has been designed | 10:30 | 11:30
|  |  | Profile Accounting page has been created | 11:36 | 12:50
|  |  | Daily Account Balance page has been designed | 12:50 | 14:45
|  |  | Deposit / Widthrawal page has been made | 14:45 | 16:30
|  |  | Admin Email page has been created | 16:40 | 17:30
|  |  | User Emails page has been designed | 17:30 | 18:15
2024-06-24 | Monday | Admin Panel / UI Design | Administrators roles page has been created | 9:30 | 10:50
|  |  | Summary page has been designed | 10:50 | 11:30
|  |  | Administrators Statistics page has been created | 11:36 | 12:50
|  |  | Administators Beta page has ben designed | 12:50 | 14:30
|  |  | Audit Users page has ben designed | 14:30 | 16:30
|  |  | Metrics System page has been created | 16:40 | 17:15
2024-06-25 | Tuesday | Neo Connect Project | Fixing bugs for Admin and user panel | 9:30 | 18:30
2024-06-26 | Wednesday | Neo Connect Project / Ecommerce Module | Added payment page | 9:30 | 11:30
|  |  | Ecommerce List page has been created | 11:36 | 13:30
|  |  | Remove colorButton unneccesarry code from project | 13:30 | 18:15
2024-06-27 | Thursday | Neo Connect / Ecommerce Module | ITIO payment gateway has been added in user panel | 9:30 | 13:40
|  |  | Response Page has been created | 14:15 | 16:30
|  |  | Fix bug in entire user panel | 16:40 | 18:30
2024-06-28 | Friday | Neo Connect / Ecommerce Module | Ecommerce Invoice create page has been added | 9:30 | 10:00
|  |  | Ecommerce create api has been added | 10:00 | 10:30
|  |  | Delete and edit api has been created | 10:30 | 11:00
|  |  | Get details of ecommerce with list api has been added | 11:00 | 11:30
|  |  | Create and list api has been integrated on user panel | 11:36 | 13:45
|  |  | Validation on creation and other things done in user panel | 14:15 | 18:30
2024-06-29 | Saturday | Neo Connect / Ecommerce Module | Payment page design and created | 9:30 | 10:00
|  |  | Payment Realated new API's created | 10:00 | 18:30

## July 2024
Date | Day | Project Name | Tasks | Start Time | End Time | Status | Assigned By | Assigned To | Assigned Date | Expected Date | Remarks
2024-07-01 | Monday | Neo Connect / Ecommerce Module | Payment Related API's has been modified | 9:30 | 10:00
|  |  | Ecommerce create api modification has been added | 10:00 | 10:30
|  |  | Delete and edit api modification has been created | 10:30 | 11:00
|  |  | Get details of ecommerce with list api has been added | 11:00 | 11:30
|  |  | Create and list api has been modified | 11:36 | 16:30
|  |  | Transaction updated page created and api also integrated | 16:40 | 18:15
2024-07-02 | Tuesday | Neo Connect / Crypto Module | Create new Vault Account Api has been implemented | 9:30 | 13:45
|  |  | Create wallet Address api (Fireblock) has been implemented | 14:15 | 18:30
2024-07-03 | Wednesday | Neo Connect / Crypto Module | Wallet add request api has been modified | 9:30 | 10:30
|  |  | Wallet request api has been integrated on crypto page | 10:30 | 11:45
|  |  | Add Vault Account API has been also integrated | 11:45 | 14:45
|  |  | Vault Account Id field has been added in User Model table | 14:45 | 16:30
|  |  | Get Wallet Address for specific coin has been added on crypto page | 16:40 | 18:30
2024-07-04 | Thursday | Neo Connect / Crypto Module | Currency Type field added in both api and in frontend crypto page | 9:30 | 10:40
|  |  | Validation put for buy crypto | 10:40 | 11:55
|  |  | Update balance when crypto transaction sccessfully done | 12:00 | 14:50
|  |  | Transactions list api has been created | 14:50 | 16:30
|  |  | Transactions list on table in admin | 16:40 | 17:30
|  |  | Symbol Of Currency added with amount value in crypto page | 17:30 | 18:30
2024-07-05 | Friday | Neo Connect / Crypto Module | Buy API has been created | 9:30 | 10:00
|  |  | But Swap API has been implemented on Frontend Spot Trade page | 10:00 | 10:50
|  |  | Get List of Open Orders API has been created | 10:50 | 12:10
|  |  | Get List Open Orders API has been integrated on spot trade page | 12:10 | 13:30
|  |  | Sell Swap Order API has been created | 14:20 | 16:30
|  |  | Sell Swap Order API has been integrated on Spot Trade Page | 16:40 | 18:15
2024-07-08 | Monday | ******************************* | LEAVE
2024-07-09 | Tuesday | NeoConnect / Ecommerce Payment Gateway | Create Ecommerce payment gateway page for admin | 9:30 | 10:00
|  |  | Create routes for all possible api for admin ecommerce payment page | 10:00 | 11:30
|  |  | Add Money with update api has been updated (Bug) | 11:36 | 12:45
|  |  | Amount Range has been added on Spot Trade Page | 12:45 | 14:50
|  |  | Dynamically calculate the no of coins through amount range select | 14:50 | 16:30
|  |  | Ecommerece Payment gateway error has been resolved | 16:30 | 18:30
2024-07-10 | Wednesday | NeoConnect Project / UI Design | Razorpay UPI payment has been integrated on Add Money Dashboard Page and RazorPay API has been created | 9:30 | 16:30
|  |  | Transaction API and Transaction List Page has been modified | 16:40 | 18:30
2024-07-11 | Thursday | NeoConnect Project / UI Design | Bank Transfer Request list page has been created and show list of request | 9:30 | 10:00
|  |  | Admin can update the status from Bank Transfer Request List Page | 10:00 | 12:00
|  |  | API has been created for above request | 12:00 | 16:55
|  |  | UI create for user profile page from scratch | 16:55 | 18:30
2024-07-12 | Friday | NeoConnect Project / UI Design | User Login Session Hsitory page has been created with dynamic data listing done | 9:30 | 11:45
|  |  | Update User Details api has been added and list on User Profile Page | 11:45 | 16:30
|  |  | Profile Pic Modal created and update api has been created for upload profile photo of User | 16:30 | 18:30
2024-07-15 | Monday | NeoConnect Project / UI Design | Beneficary List api has been created | 9:30 | 10:00
|  |  | Beneficary List has been list on Page User Profile | 10:00 | 10:30
|  |  | Add Money Deposit fee and conversion concept added | 10:30 | 18:25
2024-07-18 | Thursday | NeoConnect Project / UI Dsign with Development | Add Money api has been modified | 9:30 | 10:00
|  |  | Till date work has been pushed on live project | 10:00 | 16:30
|  |  | SSL certificate has been installed on live url | 16:40 | 18:25
Live Url Link for User Panel is https://quickcash.oyefin.com/myapp
Live Url Link for Admin is https://quickcash.oyefin.com/myapp
2024-07-19 | Friday | Neo Connect Project / UI Design With Development | Add Money api has been modifed | 9:30 | 10:00
|  |  | Transaction Api has been modified | 10:00 | 10:20
|  |  | Fee Structure design has been designed and don also dynamic | 10:20 | 13:45
|  |  | Seeder has been cerated for admin, fee structure | 14:15 | 17:30
|  |  | Fee has been included on add money and exchange sections | 17:30 | 18:30
2024-07-20 | Saturday | Neo Connect Project / UI Design With Development | Transaction popup work has been completed | 9:30 | 10:50
|  |  | User Details Page has been created in Admin | 10:50 | 15:30
|  |  | User Details Page API has been integrated in Admin | 15:30 | 18:30:00 PM
2024-07-22 | Monday | Neo Connect Project / UI Design With Development | Minimum Amount vaule is added on Fee Structure Table | 9:30 | 10:39
|  |  | Custom Hook is created for getting fees commission values | 10:39 | 11:00
|  |  | Deposit and exchange fees calculation fees revise on pages | 11:00 | 18:30
2024-07-23 | Tuesday | Neo Connect Project / UI Design With Development | Transaction Pop Up details bug has been fixed | 9:30 | 12:30
|  |  | Transaction Pop Up Details has been added on modal box in Bank Transfer Request Page on Admin | 12:30
2024-07-24 | Wednesday | Neo Connect Project / UI Design With Development | Change Password with OTP validation has been done on User Profile Page | 9:30 | 11:30
|  |  | Send Email API has been created | 11:36 | 11:50
|  |  | Send Email OTP template has been created | 11:50 | 12:00
|  |  | Auth Hook has been created with private route path for User Panel | 12:00 | 12:15
|  |  | KYC page has been modified for Admin | 12:15 | 14:30
|  |  | External Transfer Payment page has been created | 14:30 | 18:20
2024-07-25 | Thursday | Neo Connect Project / UI Design With Development | External Transfer Dynamic part is done | 9:30 | 18:30
2024-07-26 | Friday | Neo Connect Project / UI Design With Development | Transfer Popup details bug fixed | 9:30 | 12:30
|  |  | Send Money to Beneficary big fixed | 12:30 | 18:30
2024-07-29 | Monday | Neo Connect Project / UI Design With Development | Send Beneficiary amount transfer from Source Account | 9:30 | 12:30
|  |  | Transaction pop up info updated (Admin) | 12:30 | 14:45
|  |  | Transaction pop up info updated (User) | 14:45 | 16:50
|  |  | Card Pin Change Modal has been designed and Made Support API for Card Change Pin | 16:50 | 18:30
2024-07-30 | Tuesday | Neo Connect Project / UI Design With Development | Stripe Payment gateway added on Add Money Section Page | 9:30 | 16:30
|  |  | Stripe add transatcion api has been created | 16:40 | 17:40
|  |  | Pop Up Transaction page has been modified with Correct Values | 17:40 | 18:20
2024-07-31 | Wednesday | Neo Connect Project / UI Design With Development | Exchange Transaction amont make editable now | 9:30 | 15:50
|  |  | Modified Exchange Transaction API | 15:50 | 18:15

## Aug 2024
Date | Day | Project Name | Tasks | Start Time | End Time | Status | Assigned By | Assigned To | Assigned Date | Expected Date | Remarks
2024-08-01 | Thursday | Neo Connect Project / UI Design With Development | Exchange Transaction amont make editable now | 9:30 | 15:50
|  |  | Modified Exchange Transaction API | 15:50 | 17:30
|  |  | Modified Dashboard Design | 17:30 | 18:30
2024-08-02 | Friday | Neo Connect Project | Dashboard Page has been modified | 9:30 | 11:30
|  |  | User Panel Sidebar has been re created | 11:30 | 13:45
|  |  | Side bar tab Statements and Total Transactions tb has been created | 14:15 | 15:30
|  |  | Get Statement api has been created for above page | 15:30 | 17:30
|  |  | Export functionality done like pdf and excel | 17:30 | 18:15
2024-08-05 | Monday | Neo Connect Project | Add Account / Edit Account page modified | 9:30 | 10:00
|  |  | Add Account/ Edit Api has been modified | 10:00 | 10:10
|  |  | generate account number serial wise funciton implemented | 10:10 | 10:15
|  |  | Invoice Page has been modified (60%) Completed | 10:15 | 17:30
|  |  | Invoice Email has been sent on invoice generation | 17:00 | 18:30
2024-08-06 | Tuesday | Neo Connect Project | Invoice in user Panel Completed | 9:30 | 2:45PM
|  |  | Invoice section in Admin Panel also completed | 14:45 | 18:30
2024-08-07 | Wednesday | Neo Connect Project | Crypto Buy/Sell Task Completed | 9:30 | 10:45
|  |  | Create request for buy.selll api has been created | 10:45 | 12:10
|  |  | Wallet Section page has been completed | 12:10 | 13:45
|  |  | Create wallet address through fireblocks third party api has been inegrated for wallet | 14:15 | 16:50
|  |  | Transaction pop up updated for crypto in Admin Panel | 16:50 | 18:15
2024-08-08 | Thursday | Neo Connect Project | Wallet Address fetch error fixed | 9:30 | 12:30
|  |  | Logo on invoice error fixed | 12:30 | 15:30
|  |  | Total Transactions filter error fixed | 15:30 | 17:45
|  |  | Invoice Settings fetch details api has been created | 17:45 | 18:30
2024-08-09 | Friday | Neo Connect Project | Transaction list modified in All Transactions Page in User Panel | 9:30 | 10:00
|  |  | Transaction list modified in Statements Page in User Panel | 10:00 | 10:15
|  |  | Added beneficiary module | 10:15 | 13:45
|  |  | Add Confirm pop up option in beneficiary payment page | 14:15 | 14:30
|  |  | Invoice due date validation has been added | 14:30 | 16:50
|  |  | Put start and due date validation on Invoice | 16:50 | 18:10
2024-08-12 | Monday | Neo Connect Project | All Account Exchange bug fixed | 9:30 | 10:00
|  |  | Transaction list header has been done bold as suggested | 10:00 | 10:05
|  |  | Revenue Page has been created on Admin Side | 10:04 | 14:45
|  |  | Revenue List with total amount earned API has been completed | 14:45 | 18:19
2024-08-13 | Tuesday | Neo Connect Project | Crypto Buy/Sell Bug fixed | 9:30 | 13:45
|  |  | Add Transaction during crypto buy/sell transaction updation | 14:15 | 17:45
|  |  | No of coins updated after successfully transaction completed | 17:45 | 18:20
2024-08-14 | Wednesday | Neo Connect Project | Kyc restriction for new users added on User Panel Page | 9:30 | 14:45
|  |  | Kyc updated details not showing on user profile page bug is fixed | 14:45 | 17:00
|  |  | Crypto buy/sell testing done | 17:00 | 18:15
|  |  | Code updated on live till date | 18:15 | 18:20
2024-08-16 | Friday | Neo Connect Project | Kyc update message details on User Dashboard page according to the kyc status | 9:30 | 10:30
|  |  | Revenue page bug fixed | 10:30 | 12:45
|  |  | Ticket design has been modified with bug fixed | 12:45 | 16:30
|  |  | Admin page has been dynamically done | 16:30 | 18:30
2024-08-20 | Tuesday | Neo Connect Project | Responsive design of Admin Dashboard | 10:00 | 12:30
|  |  | Latest record fetch in Admin user list bug fixed | 12:30 | 13:14
|  |  | Stripe Error fixed | 13:14 | 15:00
|  |  | Testing and solving bugs | 15:00 | 18:30
2024-08-21 | Wednesday | Neo Connect Project | Testing and Solving bugs on Live Website | 9:30 | 16:30
|  |  | Invoice page has been removed from Admin Panel | 16:30 | 16:35
|  |  | Fee Details page fields has been modified as per discussion in meeting | 16:35 | 17:00
|  |  | Unique Ticket Id has been generated | 17:00 | 18:30
2024-08-22 | Thursday | Neo Connect Project | Email, Primary and Secondary Phone Number verification functionality has been implemented | 9:30 | 14:55
|  |  | Invoice Setting has been modified | 14:55 | 18:00
|  |  | Image upload icon and validation has been done on KYC page | 18:00 | 18:30
2024-08-23 | Friday | Neo Connect Project | Toggle Theme Functionality has been implemented on following pages | 9:30 | 18:30
1) Dashboard page
2) Cards
3) Total Transactions
4) Statements
5) Crypto - (Wallet Address , Buy / Sell Page)
6) User Profile Page
7) Tickets
8) Refer & Earn
9 Invoices
|  |  | Kyc upload image before after design has been modified | 9:30 | 10:55
2024-08-26 | Monday | Neo Connect Project | Support/Ticket api has been created | 10:55 | 12:30
|  |  | Support/Ticket get details and chat history api has been created | 12:30 | 14:45
|  |  | Ticket Page has been modified in Admin Page | 14:45 | 16:30
|  |  | Help Center page has modified in User Panel | 16:30 | 18:30